## Table 1
Sr. No. | Discussed Point | Current Status | Next Action Plan | Remark
1 | Lift ARD System is not working | All payment done by Society. | Mr.Mahale will installing it in next week. | completed in next week.
3 | UPS & Batteries - Inverter is not working |  |  | done
4 | CCTV Camera not in working condition |  |  | ????
5 | PV Solar - Net metering not working | application submitted in otur office. Process is going on. |  | Processing…
6 | Outdoor Gym Equipments minor repairing work | Outdoor Gym Equipments is in good condition, need to replace handle grips |  | done
7 | Outdoor Childrens Play Equipements repairing work | Merry Go is brocken from bottom. Welding work is pending only. |  | Welder Require
8 | Flow Restrictor / Water Aerator need to Fixed to save water | Flow Restrictor / Water Aerator need to Fixed in each flat to reduce water consumption |  | Pending…
9 | Society all maintanance, housekeeping and expenses part need to take in Shubham's scope | Need to discuss with Society peoples and take all maintanance, housekeeping and expenses part need to take in Shubham's scope |  | cancel…
10 | Plantation and Landscaping repairing work |  |  | done
11 | Water Treatment Plant one standby pump not fixed |  |  | done
12 | WTP Revamping work |  |  | done
13 | New Guardner appointment | Need to appoint new guardner for landscaping work repairing |  | cancel…
14 | New Property Supervisor appointment | appointed and joined by Mr.Mangessh Gunjal |  | done
15 | Utility water pressure not come to Row House holders | all material is ready. |  | plumber Require
16 | Water Scaling unit not working (Softner Unit) |  |  | done
17 | Water metering not working | Need to make water scaping unit operational to avoid this choke-up issue |  | Processing…
18 | STP, WTP, Hydro-pneumatic system few pumps not found at site and not working | 3motors are for maintenance in pune and 3 are missing from tarangan site. | For WTP pressure pump is arranged by society and for STP our 3 repaired motor will installed | Processing…
19 | Solar Water Heater timers not found at site | it is all in brocken conditions. | no need to re-install it in phase I | cancel…
20 | Roadside compound wall paiting work | Need to check the roadside compound wall painting area, Order material and make it paint |  | Pending…
21 | Street Light & parking lights not working | parking light work is comleted only sreet light work is pending. |  | Electrician Require
22 | OWC Machine not working | motor shaft is brocken and rubber beading leakges. Gear box allignment also have to checked. | motor shaft is getting on Sunday. Motor will be ready and assembled on same day. Calling to Earth Care for next repairing work. | Processing…
23 | OWC Machine working video need to share, awareness about dry and wet waste in society peoples | ppt is almost ready… | after running machine we will make a real operational video and then aware the peoples for waste collection and segregation. Along with benefits of composting. | Processing…
24 | Installation of Do & Don't boards near WTP, STP & OWC | Need to install Do & Don't boards near WTP, STP & OWC | its being prepaired. It will placed untill all plants are running | Processing…
25 | Supply to Outsource Drinking Water | Supply to Outsource Drinking Water |  | Processing…
26 | Water seepages & Leckages problem in Phase 1 | material are ready | workers | ?????
27 | New 2 Borewell Need to take in site premises |  |  | done
28 | Pimpalwandi Well water should reach at site | line is repaired. New NRV and air valve are installed. | well water is over flowed from well so waiting for decrease the water level. | Processing…
29 | Drainage Line from Shubham Tarangan to Vadgaon Anand |  |  | Pending…
30 | Phase 1 all strom waterline need to clean and remove choke-up problem |  | we are going to call Mr.satish for cleaning and break the strom waterline. | Processing…
31 | Nearest water source source arrangement | meet and followed up with Mr.Gandhi Sir. | We have to discuss with Mr.Pattekari | Processing…
32 | Main Entrance Gate Logo |  |  | Processing…
33 | STP Revamping work - Pump, Pipes & System only | all materials are ready. | relay is yet to come. PO is done. | Electrician Require
34 | STP Revamping work - Civil Work | To take new tank working drawings from WTE person, to arrage their site visit, And to start existing STP immediately till the revamping work completed on site |  | ?????
35 | Club House - Civil Work | Club Hous extension work should be completed on site till July end | Nagarkar sir informed it will ready up to 27th aug. we take it with reday to use condition for society Ganpati Festival | Processing…
36 | Project East side entrance gate renevation work | civil and painting work is completed |  | ????
37 | Y strainer installation | all materials are ready. |  | plumber Require
36 | Project East side entrance gate renevation work | civil and painting work is completed |  | ????

## Table 2
Sr. No. | Discussed Point | Action To be taken | Estimated cost | Actual Cost | Responsible Person 1 | Responsible Person 2 | Previous Deadline | Remark on 11/06/2022 | Responsible Person 2 | New Deadline | Remark on 19/07/2022
23 | OWC Machine working video need to share, awareness about dry and wet waste in society peoples | Give Dry & Wet Dustbin to society, collect separate waste, use site wet waste for OWC machine, awareness program, video, compost using for landscaping work | 75000 |  | Rohini Vite | Kiran Nagarkar | 2022-05-20 | DARY AND WET dust bin not yet ordered | Rohini Vite / Keshav Ghule | 2022-07-30 | PR given of all dust bins, we will distribute in society and aware them about the benifits of OWC Machine & Its working.
24 | Installation of Do & Don't boards near WTP, STP & OWC | Need to install Do & Don't boards near WTP, STP & OWC | [6 empty] | Keshav Ghule | 2022-07-30 | Need to install Do & Don't boards near WTP, STP & OWC
25 | Supply to Outsource Drinking Water | Supply to Outsource Drinking Water |  |  | Avinash Fulsundar | Kiran Nagarkar | 2022-03-15 | Not required now, previous water agency payment is pending. |  |  | Currently Existing borewell water is sufficient so no need to outsourced water
26 | Water seepages & Leckages problem in Phase 1 | Need to make site visit and make it repair with proper solution and work methodology | [6 empty] | Rohini Vite | 2022-07-30 | Site visit done by Shivaji Mate, Work will be start from 23/07/2022
|  | Total - 1 | 1165591 | 545153
27 | New 2 Borewell Need to take in site premises | Need to take 2 new borewell in site premises | 65234 |  | Kiran Nagarkar | Kiran Nagarkar/She khar Waghule | 2022-03-15 | work completed | Keshav Ghule |  | work completed
28 | Pimpalwandi Well water should reach at site | Need to repair the line, install NRV at required location and to reach water at site | 100000 |  | Keshav Ghule | Shekhar Waghule | 2022-05-18 | working on it, Ajay Sanas and team is coming at site on Monday they will work 2 days on site to sort-out the problem. All leakages and other part is resolved. | Keshav Ghule | 2022-07-30 | Work in Progress also checking MGP Water arrangement and other water source from local
29 | Drainage Line from Shubham Tarangan to Vadgaon Anand | [7 empty] | Keshav Ghule |  | Work will be start after mansoon
30 | Phase 1 all strom waterline need to clean and remove choke-up problem | [6 empty] | Phase 1 all strom waterline need to clean and remove choke-up problem | Keshav Ghule | 2022-07-30 | Phase 1 all strom waterline need to clean and remove choke-up problem
31 | Nearest water source source arrangement | [7 empty] | Keshav Ghule / Shekhar Waghule | 2022-08-15 | Work in Progress also checking MGP Water arrangement and other water source from local
32 | Main Entrance Gate Logo | [7 empty] | Shekhar Wahule | 2022-08-15 | Designin work started will complete the work till 15 August
33 | STP Revamping work - Pump, Pipes & System only |  | 1540000 |  | Kiran Nagarkar | Kiran Nagarkar/She khar Waghule | 2022-05-20 | Pumps is working need to make advance for STP work | Keshav Ghule |  | All pump is started and in working condition, need to clean the tanks and ask WTE team for completion of their scope of work
34 | STP Revamping work - Civil Work | To take new tank working drawings from WTE person, to arrage their site visit, And to start existing STP immediately till the revamping work completed on site |  |  | Kiran Nagarkar | Kiran Nagarkar/She khar Waghule | 2022-05-20 | All drawings received from WTE but RCC working drawings not yet received from PS Kulkarni Associates | Kiran Nagarkar |  | All drawings received from WTE but RCC working drawings not yet received from PS Kulkarni Associates
35 | Club House - Civil Work | Club Hous extension work should be completed on site till July end |  |  | Kiran Nagarkar | Kiran Nagarkar | 2022-07-15 | Work started but speed is very slow | Kiran Nagarkar |  | Work started but speed is very slow
Sr. No. | Discussed Point | Action To be taken | Estimated cost | Actual Cost | Responsible Person 1 | Responsible Person 2 | Previous Deadline | Remark on 11/06/2022 | Responsible Person 2 | New Deadline | Remark on 19/07/2022
36 | Project East side entrance gate renevation work | Need to complete repairing work of Project East side entrance gate / renevation work |  |  | Kiran Nagarkar | Kiran Nagarkar | 2022-05-25 | Previous ACP removed, work yet not started | Kiran Nagarkar
|  | Total - 2 | 1705234 | -